## F-001967
ACC | Checklist | Validation on | State | Estimated | Covered by | Build # | Browser |  |  |  | OC
[7 empty] | Edge18 | Chrome79 | FF72 | IE11
F-001967 Provide a table UI to view/edit Usage Conditions
I-014800 "Add Usage Condition Table Editor sidebar tab for Component item"
There is Side Bar on Variable Component Item form. | Check that when you Open Variable Component there is Side bar | Certification | Done | 1 | Manual | 150 | Anastasia | Anastasia | Anastasia | Anastasia | Win10
| Check that when you Create Variable Component there is Side Bar | Certification | Done | 1 | Manual | 150 | Anastasia | Anastasia | Anastasia | Anastasia
| Check that after you Edit and Save Variable Component there is Side Bar | Certification | Done | 1 | Manual | 150 | Anastasia | Anastasia | Anastasia | Anastasia
| Check that after you Edit and Done Variable Component there is Side Bar | Certification | Done | 1 | Manual | 150 | Anastasia | Anastasia | Anastasia | Anastasia
When user create or open Variable Component Item THEN Variable Component Item form is displayed. | Check that when you Open Variable Component the Variable Component Item form is displayed | Certification | Done | 1 | Manual | 150 | Anastasia | Anastasia | Anastasia | Anastasia
| Check that when you Create Variable Component the Variable Component Item form is displayed | Certification | Done | 1 | Manual | 150 | Anastasia | Anastasia | Anastasia | Anastasia
| Check that after you Edit and Save Variable Component the Variable Component Item form is displayed | Certification | Done | 1 | Manual | 150 | Anastasia | Anastasia | Anastasia | Anastasia
| Check that after you Edit and Done Variable Component the Variable Component Item form is displayed | Certification | Done | 1 | Manual | 150 | Anastasia | Anastasia | Anastasia | Anastasia
When user hovers over Variable Component Item tab on SideBar THEN "Form of Variable Component Item 'Name of Variable Component Item'" tooltip is displayed. | Confirm that in opened Variable Component there is tooltip when you hovers over Variable Component Item Tab | Certification | Done | 1 | Manual | 150 | Anastasia | Anastasia | Anastasia | Anastasia
| Confirm that in created Variable Component there is tooltip when you hovers over Variable Component Item Tab | Certification | Done | 1 | Manual | 150 | Anastasia | Anastasia | Anastasia | Anastasia
| Check that tooltip is "Form of Variable Component 'Keyed Name' " | Certification | Done | 1 | Manual | 150 | Anastasia | Anastasia | Anastasia | Anastasia
| Check that Variable Component Item Tab is the first tab in Side Bar | Certification | Done | 1 | Manual | 150 | Anastasia | Anastasia | Anastasia | Anastasia
There is blank Table Editor tab in Variable Component item as second sidebar tab. | Confirm that when you Open Variable Component, the Table Editor tab is second in Side Bar | Certification | Done | 1 | Manual | 150 | Anastasia | Anastasia | Anastasia | Anastasia
| Confirm that when you Create Variable Component, the Table Editor tab is second in Side Bar | Certification | Done | 1 | Manual | 150 | Anastasia | Anastasia | Anastasia | Anastasia
| Confirm that when you Saved/Done Variable Component, the Table Editor tab is second in Side Bar | Certification | Done | 1 | Manual | 150 | Anastasia | Anastasia | Anastasia | Anastasia
When user hovers over Table Editor tab on SideBar THEN "Usage Condition Table Editor" tooltip is displayed. | Check that in opened Variable Component there is tooltip "Usage Condition Table Editor" when you hovers over Table Editor tab | Certification | Done | 1 | Manual | 150 | Anastasia | Anastasia | Anastasia | Anastasia
| Check that in created Variable Component there is tooltip "Usage Condition Table Editor" when you hovers over Table Editor tab | Certification | Done | 1 | Manual | 150 | Anastasia | Anastasia | Anastasia | Anastasia
| Check that after saved/done Variable Component there is tooltip "Usage Condition Table Editor" when you hovers over Table Editor tab | Certification | Done | 1 | Manual | 150 | Anastasia | Anastasia | Anastasia | Anastasia
I-014804 "Variability Item field for Table Editor sidebar tab of Component"
There is "Variability Item" Item field in Settings panel of Usage Conditions Table Editor sidebar tab. | Check that in Usage Conditions Table there is "Variability Item" Item field | Certification | Done | 1 | Manual | 150 | Anastasia | Anastasia | Anastasia | Anastasia | Win10
| "Variability Item" item field locates similary to Breakdown Item form | Certification | Done | 1 | Manual | 150 | Anastasia | Anastasia | Anastasia | Anastasia
User can pick Variability Item using this item field. | Check that you can select Variability Item when click on '...' button | Certification | Done | 1 | Manual | 150 | Anastasia | Anastasia | Anastasia | Anastasia
| Check that you can select Variability Item when begin type their number of component in field | Certification | Done | 1 | Manual | 150 | Anastasia | Anastasia | Anastasia | Anastasia
| Check that you can select new Variability Item when old already selected (delete) | Certification | Done | 1 | Manual | 150 | Anastasia | Anastasia | Anastasia | Anastasia
| Check that you can select new Variability Item when old already selected ('…' button) | Certification | Done | 1 | Manual | 150 | Anastasia | Anastasia | Anastasia | Anastasia
| Check that you can't select two or more Variability Items at the same time ('…' button) | Certification | Done | 1 | Manual | 150 | Anastasia | Anastasia | Anastasia | Anastasia
| Type invalid data in field | Certification | Done | 1 | Manual | 150 | Anastasia | Anastasia | Anastasia | Anastasia
I-014803 "Add splitter for Usage Condition table editor in Component item"
Splitter should split the area into 2 parts in usage condition table editor sidebar tab. | Confirm the splitter splits the area into 2 parts in Resolution sidebar tab | Certification | Done | 1 | Manual | 155 | Anastasia | Anastasia | Anastasia | Anastasia | Win10
| Confirm that size of left pannel is 305px |  | Done | 1 | Manual | 155 | Anastasia | Anastasia | Anastasia | Anastasia
User can select splitter using LMB and move it to the right or to the left side. | Confirm the User can select splitter using LMB | Certification | Done | 1 | Manual | 155 | Anastasia | Anastasia | Anastasia | Anastasia
| Confirm that User can move splitter to the left side | Certification | Done | 1 | Manual | 155 | Anastasia | Anastasia | Anastasia | Anastasia
| Confirm that User can move splitter to the right side | Certification | Done | 1 | Manual | 155 | Anastasia | Anastasia | Anastasia | Anastasia
I-014965 “Implement formatter for grid header”
Header with features and options is displayed on a test page. | Confirm that header with features and options is displayed | Certification | Done | 1 | Manual | 167 | Anastasia | Anastasia | Anastasia | Anastasia | Win10
| Confirm that there is first empty column | Certification | Done | 1 | Manual | 167 | Anastasia | Anastasia | Anastasia | Anastasia
| Confirm that the color of the feature’s header cell is #EEEEEE | Certification | Done | 1 | Manual | 167 | Anastasia | Anastasia | Anastasia | Anastasia
| Confirm that the color of the option’s header cell i#F7F7F7 | Certification | Done | 1 | Manual | 167 | Anastasia | Anastasia | Anastasia | Anastasia
If name of Feature more that width of column in grid THEN display feature name with ... in the ending of column. | Confirm that when header long it cut off to ”…” | Certification | Done | 1 | Manual | 167 | Anastasia | Anastasia | Anastasia | Anastasia
If name of Option more that height of column in grid THEN display option name with ... in the top of column. | Check that when name of option more that hight of column in grid it cut off to "…" | Certification | Done | 1 | Manual | 167 | Anastasia | Anastasia | Anastasia | Anastasia
| Check when you change size of column | Certification | Done | 1 | Manual | 167 | Anastasia | Anastasia | Anastasia | Anastasia
| Check that feature text is bold | Certification | Done | 1 | Manual | 167 | Anastasia | Anastasia | Anastasia | Anastasia
I-014807 “Create formatter for table options”
GIVEN user stays on test page; WHEN user clicks on cell THEN cell is marked as selected by blue dot. | Cliks in cell -> cell is marked as selected by blue (0303B0) dot | Certification | Done | 1 | Manual | 170 | Anastasia | Anastasia | Anastasia | Anastasia | Win10
| Cliks in cell -> sell have blue (0303B0) stroke | Certification | Done | 2 | Manual | 170 | Anastasia | Anastasia | Anastasia | Anastasia
| Cliks in cell -> string have yellow color | Certification | Done | 2 | Manual | 170 | Anastasia | Anastasia | Anastasia | Anastasia
GIVEN user stays on test page; WHEN user clicks on marked cell THEN blue dot is disappeared from cell. | Clicks on marked cell -> blue dot is disappeared from cell | Certification | Done | 1 | Manual | 170 | Anastasia | Anastasia | Anastasia | Anastasia
| Clicks on marked cell -> blue stroke | Certification | Done | 1 | Manual | 170 | Anastasia | Anastasia | Anastasia | Anastasia
Other Checks | Check that formatter have three yellow color how in grid | Certification | Done | 1 | Manual | 170 | Anastasia | Anastasia | Anastasia | Anastasia
| Check then when cell have dot but you don't selected this cell - cell have grey (F7F7F7) color | Certification | Done | 2 | Manual | 170 | Anastasia | Anastasia | Anastasia | Anastasia
| Check how look dot when you resize the features header | Certification | Done | 1 | Manual | 170 | Anastasia | Anastasia | Anastasia | Anastasia
| Check that when cell haven't dot and you don't selected this cell -> white color | Certification | Done | 1 | Manual | 170 | Anastasia | Anastasia | Anastasia | Anastasia
Bug | Cells in the formatter are shifting | Certification | Done | 5 | Manual | 170 | Anastasia | Anastasia | Anastasia | Anastasia
I-014805 "Populate grid with header when variability item is changed"
GIVEN user in Usage Conditions Table Editor sidebar tab; WHEN user selected Variability item THEN grid header with features and options is displayed in the right split pane. | Select VI (F2) -> Confirm that in the right split panel the grid header with features and options is displayed | Certification | Done |  | Manual | 167 | Anastasia | Anastasia | Anastasia | Anastasia | Win10
| Select VI (...) -> Confirm that in the right split panel the grid header with features and options is displayed |  | Done |  | Manual | 167 | Anastasia | Anastasia | Anastasia | Anastasia
| Select VI (Type) -> Confirm that in the right split panel the grid header with features and options is displayed |  | Done |  | Manual | 167 | Anastasia | Anastasia | Anastasia | Anastasia
| Move spliter -> the grid header with features and options does not deformable |  | Done |  | Manual | 167 | Anastasia | Anastasia | Anastasia | Anastasia
Verify that displayed features and options are belong to selected Variability item. | Select (...) first VI -> confirm that displayed features and options are belong to selected VI | Certification | Done |  | Manual | 167 | Anastasia | Anastasia | Anastasia | Anastasia
| Change structure of the first VI -> select first VI -> confirm that displayed features and options are belong to selected VI |  | Done |  | Manual | 167 | Anastasia | Anastasia | Anastasia | Anastasia
[5 empty] | Manual | 167 | Anastasia | Anastasia | Anastasia | Anastasia
GIVEN user selected Variability item and grid header is displayed in the right split pane; WHEN user clears Variability item field THEN right split pane is empty. Grid header disappears from the right split pane. | Delete text in VI field -> Right split pane is empty | Certification | Done |  | Manual | 167 | Anastasia | Anastasia | Anastasia | Anastasia
| Delete text in VI field -> Grid header disappears from the right split pane | Certification | Done |  | Manual | 167 | Anastasia | Anastasia | Anastasia | Anastasia
[7 empty] | Anastasia | Anastasia | Anastasia | Anastasia
GIVEN user selected Variability item and grid header is displayed in the right split pane; WHEN user re-selects another variability item THEN grid header with features and options belongs to re-selected variability item is displayed in the right split pane. | Select (F2) second VI -> Confirm that grid header with features and options belongs to re-selected variability item is displayed in the right split pane | Certification | Done |  | Manual | 167 | Anastasia | Anastasia | Anastasia | Anastasia
[7 empty] | Anastasia | Anastasia | Anastasia | Anastasia
The features (columns) are displayed in alphabetical order. | Confirm that the features columns are displayed in alphabetical order | Certification | Done |  | Manual | 167 | Anastasia | Anastasia | Anastasia | Anastasia
The options (columns) are displayed in the same Sequence as specified in its associated feature. | Confirm that the options columns are displayed in the Same Sequence as specified in its associated feature | Certification | Done |  | Manual | 167 | Anastasia | Anastasia | Anastasia | Anastasia
The 1st column of the table is allocated to display pencil or warning icons, where needed. | Confirm that there is 1st column of the table and it empty | Certification | Done |  | Manual | 167 | Anastasia | Anastasia | Anastasia | Anastasia
Other Checks | Fixed header with options and features |  | Done |  | Manual | 167 | Anastasia | Anastasia | Anastasia | Anastasia
| Fixed first two columns |  |  |  | Manual | 167 | Anastasia | Anastasia | Anastasia | Anastasia
| There is horizontal scroll |  | Done |  | Manual | 167 | Anastasia | Anastasia | Anastasia | Anastasia
| There is vertical scroll |  | Done |  | Manual | 167 | Anastasia | Anastasia | Anastasia | Anastasia
| You can check/uncheck cell |  | Done |  | Manual | 167 | Anastasia | Anastasia | Anastasia | Anastasia
| Cut off name of features and options |  | Done |  | Manual | 167 | Anastasia | Anastasia | Anastasia | Anastasia
| Size of this formatter relative to the page |  | Done |  | Manual | 167 | Anastasia | Anastasia | Anastasia | Anastasia
| Check that table is equable |  | Done |  | Manual | 167 | Anastasia | Anastasia | Anastasia | Anastasia
Bug: I-015760 "Cells in the formatter are shifting"
| Cliks in cell -> cell is marked as selected by blue dot and cells doesn't shifting |  | Done | 2 | Manual | 167 | Anastasia | Anastasia | Anastasia | Anastasia | Win10
| Clicks on marked cell -> blue dot is disappeared from cell and cells doesn't shifting |  | Done | 2 | Manual | 167 | Anastasia | Anastasia | Anastasia | Anastasia
| Сlick on the side cells -> cells doesn't shifting |  | Done | 2 | Manual | 167 | Anastasia | Anastasia | Anastasia | Anastasia
I-014808 "Populate usage condition table editor grid with assets"
GIVEN user located in variable component item and there is defined default variability item for this variable component; WHEN user goes to usage condition table editor sidebar tab THEN grid is populated with related assets of this variable component. | Open VC with deafult VI -> in UCTE there is grid with assets | Certification
In VC change VI -> Save -> in UCTE there is grid with assets
GIVEN user located in variable component item and there is NO defined variability item; WHEN user goes to usage condition table editor sidebar tab THEN grid is not populated with related assets of this variable component. | Open VC without VI -> right split pane is empty | Certification
Open VC with VI -> delete VI in relship -> right split pane is empty
| Open VC with VI -> in UCTE delete VI -> right split pane is empty | Certification
Add new VI in UCTE -> Done -> Close -> Open -> right split pane is empty in UCTE
GIVEN user located in variable component item and there is NO defined variability item; WHEN user goes to usage condition table editor sidebar tab and selects variability item in variability item field THEN grid is populated with related assets of this variable component. | Open VC without VI -> in UCTE add VI -> there is grid with assets | Certification
Asset is displayed in row in the following format: Icon + keyed_name of Part or Document. | Check Part format Icon + keyed name | Certification
| Check Doc format Icon + keyed name | Certification
If keyed_name of asset more that width of column in grid THEN display keyed_name with ... in the ending of column. | Check Part cut off … | Certification
| Check Doc cut off … | Certification
GIVEN many assets are displayed that a vertical scrollbar appears in usage condition table editor sidebar tab WHEN user scrolls down list of assets THEN header with features and options is fixed. | Check in Frame VC | Certification
Other Checks | VC with def.VI -> delete some assets -> this assets deleted in table
VC with def.VI -> delete all assets -> table without assets
VC without assets -> add new VI -> table without assets
VC without assets and without VI -> right split panel is empty
VC without assets and without def.VI -> add in UCTE VI -> table without assets
Change number of part -> new value in table
Change number of doc -> new value in table
Add assets for VC with VI -> new assets in table
Add assets for VC without VI -> right split panel is empty
VC without VI -> Add VI in UCTE -> add new assets -> new assets in table
VC without VI -> Add VI in UCTE -> delete some assets -> new value in table
VC without VI -> Add VI in UCTE -> delete all assets -> no assets in table
VC without VI -> Add VI in UCTE -> add new assets -> new assets in table - close VC -> Open VC -> right split panel is empty
I-014964 "Populate usage condition table editor grid with asset usages"
GIVEN user located in variable component item and there is defined default variability item for this variable component; WHEN user goes to usage condition table editor sidebar tab THEN usage conditions of related assets are displayed in table format. | VC with def.VI -> Go to the UCTE -> Confirm that usage conditions of related assets are displayed in table formatter |  | Done | 2 | Manual | 170 | Olena | Olena | Olena | Olena | Chrome, FF 68, Edge, IE on Win 8.1 / FF60 on Win 10
GIVEN user located in variable component item and there is NO defined variability item; WHEN user goes to usage condition table editor sidebar tab THEN usage conditions of related assets are not displayed in table format. | VC withot VI -> go to the UCTE -> Confirm that usage conditions of related assets are not displayed in table formatter |  | Done |  | Manual | 170 | Olena | Olena | Olena | Olena
| VC withot VI, but with usages (delete VI -> Close -> refresh search -> Open VC)-> go to the UCTE -> Confirm that usage conditions of related assets are not displayed in table formatter |  | Done |  | Manual | 170 | Olena | Olena | Olena | Olena
| VC withot VI, but with usages (delete VI -> Close -> do not refresh search -> Open VC)-> go to the UCTE -> Confirm that usage conditions of related assets are not displayed in table formatter --- bug in innovator |  |  |  | Manual | 170 | Olena | Olena | Olena | Olena
| VC withot VI, without usages -> go to the UCTE -> Confirm that usage conditions of related assets are not displayed in table formatter |  | Done |  | Manual | 170 | Olena | Olena | Olena | Olena
GIVEN user located in variable component item and there is NO defined variability item; WHEN user goes to usage condition table editor sidebar tab and selects variability item in variability item field THEN usage conditions of related assets are displayed in table format. | VC without VI -> go to the UCTE -> Select VI -> Confirm that usage conditions of related assets are displayed in table formatter |  | Done |  | Manual | 170 | Olena | Olena | Olena | Olena
GIVEN user selected Variability item and usage conditions are displayed in the right split pane; WHEN user re-selects another variability item THEN usage conditions of related assets are displayed in table format. | VC without VI -> go to the UCTE -> Select VI -> Confirm that usage conditions of related assets are displayed in table formatter -> select new VI -> usage conditions of related assets are displayed in table format. |  | Done |  | Manual | 170 | Olena | Olena | Olena | Olena
| VC with def.VI -> Go to the UCTE -> Confirm that usage conditions of related assets are displayed in table formatter -> Select new VI -> usage conditions of related assets are displayed in table format. |  | Done |  | Manual | 170 | Olena | Olena | Olena | Olena
Combination; In F1: OP1, OP2. In F2: Op4, OP5 | F1=OP1 |  | Done |  | Manual | 170 | Olena | Olena | Olena | Olena
| F1=OP1 OR F1=OP2 |  | Done |  | Manual | 170 | Olena | Olena | Olena | Olena
| F1=OP1 AND F2=OP4 |  | Done |  | Manual | 170 | Olena | Olena | Olena | Olena
| (F1=OP1 OR F1=OP2) AND (F2=OP4) |  | Done |  | Manual | 170 | Olena | Olena | Olena | Olena
| (F1=OP1 OR F1=OP2) AND (F2=OP4 OR F2=OP5) |  | Done |  | Manual | 170 | Olena | Olena | Olena | Olena
Unvalid combination | F1=OP1 AND F1=OP2 |  | Done |  | Manual | 170 | Olena | Olena | Olena | Olena
| F1=OP1 OR F2=OP4 |  | Done |  | Manual | 170 | Olena | Olena | Olena | Olena
| F1=OP1 AND F1=OP2 OR F2=OP4 |  | Done |  | Manual | 170 | Olena | Olena | Olena | Olena
| (F1=OP1 AND F1=OP2) OR (F2=OP4 OR F2=OP5) |  | Done |  | Manual | 170 | Olena | Olena | Olena | Olena
| When two (or more) usage condition in assets |  | Done |  | Manual | 170 | Olena | Olena | Olena | Olena
| When use conditions besides OR or AND |  | Done |  | Manual | 170 | Olena | Olena | Olena | Olena
| all options from features with OR |  | Done |  | Manual | 170 | Olena | Olena | Olena | Olena
Other Checks | VC with def.VI -> add/delete new usage condition -> go to the UCTE -> confirm that new UC are not displyed -> reselect VI -> new UC displayed in table |  | Done |  | Manual | 170 | Olena | Olena | Olena | Olena
| VC without def.VI -> add/delete new usage condition -> go to the UCTE -> select VI -> new UC displayed in table |  | Done |  | Manual | 170 | Olena | Olena | Olena | Olena
Bug | VM:Error appears if usage is created for unsaved VariableCompon.
Bug in innovator | VC withot VI, but with usages (delete VI -> Close -> do not refresh search -> Open VC)-> go to the UCTE -> Confirm that usage conditions of related assets are not displayed in table formatter --- bug in innovator
I-014811 "Warning and edit icons for usages in table editor"
GIVEN user located in usage condition table editor; WHEN user has edited the condition THEN edit icon is displayed in first column of table. | Open Component -> Go to the UCTE -> click into cell -> edit icon is displayed
Open Component -> Go to the UCTE -> click into cell again -> edit icon is displayed
Create Component -> Add VI -> Go to the UCTE -> click into cell -> edit icon is displayed
Create Component -> Go to the UCTE -> click into cell again -> edit icon is displayed
Verify that user can edit usage condition only in edit mode of item. | Do to the UCTE -> user can edit usage condition only in edit mode of item.
GIVEN user has complex rule (s); WHEN user goes to usage condition table editor sidebar tab THEN warning icon is displayed in first column in table for complex rules. | Compex rule -> warning
Unvalid rule -> warning
Open VC -> add unvalid/complex rule -> warning
Open VC -> delet unvalid/compex rule -> no warning
Create VC -> add unvalid/complex rule -> warning
Unvalid VI -> select them in field in UCTE -> warning
When user hovers over warning icon THEN tooltip with text "Usage Condition too complex for this table" is displayed. | Hover over warning icon -> tooltip with text "Usage Condition too complex for this table" is displayed.
Select new VI and check warning
Select new VI and check edit icon
Warning more important that edit - the first priority (it in one VI -> select new -> warning without edit)
I-014810 "Implement grey cells in table editor"
GIVEN user has complex rule (s); WHEN user goes to usage condition table editor sidebar tab THEN row (s) is disabled with grey style. | Create VC -> Complex rule -> warning + row (s) is disabled with grey style.
Create VC -> Unvalid rule -> warning + row (s) is disabled with grey style.
Create VC -> Complex rule/unvalid rule -> select new VI -> warning + row (s) is disabled with grey style.
Open VC -> Complex rule -> warning + row (s) is disabled with grey style.
Oreate VC -> Unvalid rule -> warning + row (s) is disabled with grey style.
Oreate VC with def VI -> Complex rule/unvalid rule -> select new VI -> warning + row (s) is disabled with grey style.
Verify that user can not edit rule in disabled row. | User can not edit rule in disabled row.

## Data
State | Assign to
Backlog | Olena
In progress | Anastasia
Done |  | Acceptance Test
Pending
Stopped