## What's New
Changes | Description | Is initial Release | Feature Dependent On | Additional Notes
all | I-026857 Upgrade VM Sample App to Innovator 12.0 SP12
Features/Options | F-003820 "SampleApp: Manage relations to Feature/Option used in Expression"
VI: Form: Relevant Features | I-027604 Scroll isn't displayed in Relevant features in Validate tab (VI)
VI: Table Rule Editor | I-012447 Table RE creates incorrect rule: same option in multiple feature
I-028737 "Rules displayed as ... when return from Form tab in Table Rule"
I-028743 "Selection disappears when add one more principal or constrained"
F-003820 "SampleApp: Manage relations to Feature/Option used in Expression"
VI: Text Rule Editor | F-003820 "SampleApp: Manage relations to Feature/Option used in Expression"
VC: Usage Condition Table Editor | I-026865 Define CUI Location for Toolbar above Usage Condition Table Edit
I-026869 Define a CUI Location for Context Menu of Usage Condition Table
I-026866 Use item editor in asset colum of Usage Condition Table Editor
I-026867 Provide a public method to reload a Usage Condition Table Editor
I-026870 Provide public method to update row in Usg Condition Tabl Editor
I-028708 "No scrolls in Usage Condition Table Editor"

## TOC
New fixed issues impact
Test Case Name | Planned Time (h) | Path | Test Type | Executed | New fixed issues impact | Comments | Known issues (previous Innovator version) | Functionality issues(not by test)
VM_Sample_Smoke_Dictionary for Product Variability | 0.1 | 12SP12 for Grammer/Smoke test | smoke |  | Medium
VM Sample Smoke test_Variability_Item | 0.72 | 12SP12 for Grammer/Smoke test | smoke |  | High
VM Sample Smoke test_Breakdown_Item | 0.5 | /12SP12 for Grammer/Smoke test | smoke
VM Sample Smoke test_Variable Component | 0.5 | 12SP12 for Grammer/Smoke test | smoke |  | High
F-001053 VM Sample App Defining Feature and Option Dictionary | 0.1 | 12SP12 for Grammer/Regression tests/Dictionary for Product Variability | acceptance |  | Medium
VM Sample Variability_Item_Validation of Generic Structure | 0.6 | 12SP12 for Grammer/Regression tests/Variability Item/ | acceptance |  | High
VM Sample_Variability Item_Table Rule Editor | 0.2 | 12SP12 for Grammer/Regression tests/Variability Item/ | acceptance |  | High
VM Sample Variability_Item_Variant Tree | 0.2 | 12SP12 for Grammer/Regression tests/Variability Item/ | acceptance |  | Medium |  | I-029206
F-001054 VM Sample App Defining a variability items and structures | 0.5 | 12SP12 for Grammer/Regression tests/Variability Item/ | acceptance |  |  | 3.1.10 - Name of sidebar button should be "Form"
F-001055 VM Sample App Create and Manage Rules in Var Item Strc | 0.05 | 12SP12 for Grammer/Regression tests/Variability Item/ | acceptance | FALSE | No
F-001237 Validation side bar tab for variability item | 0.5 | 12SP12 for Grammer/Regression tests/Variability Item/ | acceptance |  | Low | 3.10, 3.11- update (TestOption2 shouldn't be red)
F-001232 Defining breakdown items and structures | 0.25 | 12SP12 for Grammer\Regression tests\Breakdown Item | acceptance |  | Low
F-001234 Resolution side bar tab for breakdown item | 0.25 | 12SP12 for Grammer\Regression tests\Breakdown Item | acceptance |  | Low
F-001421 VM: Breakdown Items to contain fixed content | 0.35 | 12SP12 for Grammer\Regression tests\Breakdown Item | acceptance |  | Low
F-001535 VM_Specify a default Variability Item for a Breakdown Item | 0.1 | 12SP12 for Grammer\Regression tests\Breakdown Item | acceptance |  | Low
F-001540 VM: Breakdown Structure resolution for selected options | 0.1 | 12SP12 for Grammer\Regression tests\Breakdown Item | acceptance |  | Low | Issue should be added to 3.3 TestCase | I-019049
F-001233 Defining component with assets tab | 0.25 | 12SP12 for Grammer\Regression tests\Variable Component | acceptance |  | Low
F-001529 VM_Specify a default Variability Item for a Component | 0.1 | VM_Sample_12_0_0_1\12SP12 for Grammer\Regression tests\Breakdown Item | acceptance |  | Low
F-001530 VM_Manage usage condition of assets on a Component | 0.5 | 12SP12 for Grammer\Regression tests\Breakdown Item | acceptance |  | Medium | 3.10:should be updated, 3.7-3.9: can be optimized
F-001660 VM Automatic manage usages form re-opening - Assets tab | 0.1 | VM_Sample_12_0_0_1\12SP12 for Grammer\Regression tests\Breakdown Item | acceptance |  | Medium
F-001876 IF.THEN.....etc from intellisense of usage editor | 0.1 | 12SP12 for Grammer\Regression tests\Breakdown Item | acceptance |  | Low
F-001967 Provide a table UI to view_edit Usage Conditions | 0.5 | 12SP12 for Grammer\Regression tests\Breakdown Item | acceptance |  | Medium
Variable Compoment_Extend functionality for Usage Condition Table Editor | 0.31 | MyI or 12SP12 for Grammer\Regression tests\Breakdown Item | acceptance |  | Low
F-001843 Component and Breakdown Item need to be versionable | 0.2 | 12SP12 for Grammer\Regression tests\Complex tests | acceptance |  | Low
I-015390 Expand for 1st lvl variability tree in VI and BDI | 0.1 | 12SP12 for Grammer\Regression tests\Complex tests | acceptance
I-024740 Prevent same child item multiple times on a parent | 0.1 | 12SP12 for Grammer\Regression tests\Complex tests | acceptance |  | Low
Manage relations to Feature and Option used in Expression | 0.2 | MyI or 12SP12 for Grammer\Regression tests\Complex tests | acceptance |  | Low
Method for update relationships from vm_ExpressionDefinition | 0.2 | MyI or 12SP12 for Grammer\Regression tests\Complex tests | acceptance
Formatters for VM | 0.1 | 12SP12 for Grammer\Regression tests\Formatters | acceptance | FALSE | No
F-001057 VM Sample App_Prepare and load sample data | 0.2 | 12SP12 for Grammer\Regression tests\Sample Data | acceptance | FALSE | No
7.98
| Smoke Tests | Regression Tests (acceptance tests)
| 1.82 | 6.16

## #211 VM Sample 12SP12
N | Tests | Owner | Planned Hours | Actual Hours | Correction | Plan (Finish) | Actual (Finish) | Result | Issues | Functionality issues(not by test) | Solution Build / Innovator build | Server / SQL Server Version | Client OS / Browser | GDPR/ Snapshot / https / SAML | Client Lang | Client TZ
VM Sample 12SP12
| VM_Sample_Smoke_Dictionary for Product Variability | Olena Zaporozhets | 0.1 | 0.1 | 0 | 2021-02-10 | 2021-02-10 | passed |  |  | 211/27963 | 2019/ 2016EXP / Belarus Standart Time | Win10/Firefox78 | OFF/OFF/OFF/OFF | English | Ukraine Standart Time
| VM Sample Smoke test_Variability_Item | Olena Zaporozhets | 0.72 | 0.72 | 0 | 2021-02-10 | 2021-02-10 | passed |  |  | 211/27963 | 2019/ 2016EXP / Belarus Standart Time | Win10/Chromium | OFF/OFF/OFF/OFF | English | Ukraine Standart Time
| VM Sample Smoke test_Breakdown_Item | Kseniya Gavrilenko | 0.5 | 0.5 | 0 | 2021-02-10 | 2021-02-10 | passed |  |  | 211/27963 | 2019/ 2016EXP / Belarus Standart Time | Win10/Firefox68 | OFF/OFF/OFF/OFF | English | Belarus Standard Time
| VM Sample Smoke test_Variable Component | Pavel Niadvetski | 0.5 | 0.5 | 0 | 2021-02-10 | 2021-02-10 | passed |  |  | 211/27963 | 2019/ 2016EXP / Belarus Standart Time | Win10/Chrome | OFF/OFF/OFF/OFF | English | Belarus Standard Time
| F-001053 VM Sample App Defining Feature and Option Dictionary | kseniya Gavrilenko | 0.1 | 0.1 | 0 | 2021-02-11 | 2021-02-11 | passed |  |  | 211/27963 | 2019/ 2016EXP / Belarus Standart Time | Win10/Chrome | OFF/OFF/ON/OFF | English | Belarus Standard Time
| VM Sample Variability_Item_Validation of Generic Structure | Olena Zaporozhets | 0.6 | 0.6 | 0 | 2021-02-11 | 2021-02-12 | passed |  |  | 211/27963 | 2016/ 2017 / Belarus Standart Time | Win10/Chromium | OFF/OFF/OFF/OFF | English | Belarus Standard Time
| VM Sample_Variability Item_Table Rule Editor | Olena Zaporozhets | 0.2 | 0.2 | 0 | 2021-02-11 | 2021-02-12 | passed |  |  | 211/27963 | 2016/ 2017 / Belarus Standart Time | Win10/Chromium | OFF/OFF/OFF/OFF | English | Belarus Standard Time
| VM Sample Variability_Item_Variant Tree | Olena Zaporozhets | 0.2 | 0.25 | 0.05 | 2021-02-11 | 2021-02-12 | passed |  | I-029206 | 211/27963 | 2016/ 2017 / Belarus Standart Time | Win10/Chromium | OFF/OFF/OFF/OFF | English | Ukraine Standart Time
| F-001054 VM Sample App Defining a variability items and structures | Kseniya Gavrilenko | 0.5 | 0.5 | 0 | 2021-02-11 | 2021-02-11 | passed |  |  | 211/27963 | 2019/ 2016EXP / Belarus Standart Time | Win10/Firefox78 | OFF/OFF/ON/OFF | English | Ukraine Standart Time
| F-001237 Validation side bar tab for variability item | kseniya Gavrilenko | 0.5 | 0.5 | 0 | 2021-02-11 | 2021-02-11 | passed |  |  | 211/27963 | 2019/ 2016EXP / Belarus Standart Time | Win10/Chrome | OFF/OFF/ON/OFF | English | Belarus Standard Time
| I-015390 Expand for 1st lvl variability tree in VI and BDI | kseniya Gavrilenko | 0.1 | 0.1 | 0 | 2021-02-11 | 2021-02-11 | passed |  |  | 211/27963 | 2019/ 2016EXP / Belarus Standart Time | Win10/Chromium | OFF/OFF/ON/OFF | English | Belarus Standard Time
| F-001232 Defining breakdown items and structures | Pavel Niadvetski | 0.25 | 0.25 | 0 | 2021-02-11 | 2021-02-11 | passed |  |  | 211/27963 | 2019/ 2016EXP / Belarus Standart Time | Win10/Firefox78 | OFF/OFF/ON/OFF | English | Belarus Standard Time
| F-001234 Resolution side bar tab for breakdown item | Pavel Niadvetski | 0.25 | 0.25 | 0 | 2021-02-11 | 2021-02-11 | passed |  |  | 211/27963 | 2019/ 2016EXP / Belarus Standart Time | Win10/Firefox68 | OFF/OFF/ON/OFF | English | Belarus Standard Time
| F-001421 VM: Breakdown Items to contain fixed content | Pavel Niadvetski | 0.35 | 0.35 | 0 | 2021-02-11 | 2021-02-11 | passed |  |  | 211/27963 | 2019/ 2016EXP / Belarus Standart Time | Win10/Chrome | OFF/OFF/ON/OFF | English | Belarus Standard Time
| F-001535 VM_Specify a default Variability Item for a Breakdown Item | Pavel Niadvetski | 0.1 | 0.1 | 0 | 2021-02-11 | 2021-02-11 | passed |  |  | 211/27963 | 2019/ 2016EXP / Belarus Standart Time | Win10/Chromium | OFF/OFF/ON/OFF | English | Belarus Standard Time
| F-001540 VM: Breakdown Structure resolution for selected options | Pavel Niadvetski | 0.1 | 0.1 | 0 | 2021-02-11 | 2021-02-11 | passed |  |  | 211/27963 | 2019/ 2016EXP / Belarus Standart Time | Win10/Firefox78 | OFF/OFF/ON/OFF | English | Belarus Standard Time
| F-001233 Defining component with assets tab | Pavel Niadvetski | 0.1 | 0.1 | 0 | 2021-02-11 | 2021-02-11 | passed |  |  | 211/27963 | 2019/ 2016EXP / Belarus Standart Time | Win10/Firefox68 | OFF/OFF/ON/OFF | English | Belarus Standard Time
| F-001529 VM_Specify a default Variability Item for a Component | Pavel Niadvetski | 0.1 | 0.1 | 0 | 2021-02-11 | 2021-02-12 | passed |  |  | 211/27963 | 2019/ 2016EXP / Belarus Standart Time | Win10/Chrome | OFF/OFF/ON/OFF | English | Belarus Standard Time
| F-001530 VM_Manage usage condition of assets on a Component | Kseniya Gavrilenko | 0.5 | 0.6 | 0.1 | 2021-02-11 | 2021-02-11 | passed |  | I-013052 | 211/27963 | 2019/ 2016EXP / Belarus Standart Time | Win10/Chromium | OFF/OFF/OFF/OFF | English | Belarus Standard Time
| F-001660 VM Automatic manage usages form re-opening - Assets tab | Pavel Niadvetski | 0.1 | 0.1 | 0 | 2021-02-11 | 2021-02-12 | passed |  |  | 211/27963 | 2016/ 2017 / Belarus Standart Time | Win10/Firefox78 | OFF/OFF/OFF/OFF | English | Ukraine Standart Time
| F-001876 IF.THEN.....etc from intellisense of usage editor | Pavel Niadvetski | 0.1 | 0.1 | 0 | 2021-02-11 | 2021-02-12 | passed |  |  | 211/27963 | 2019/ 2016EXP / Belarus Standart Time | Win10/Firefox68 | OFF/OFF/ON/OFF | English | Belarus Standard Time
| F-001967 Provide a table UI to view_edit Usage Conditions | Pavel Niadvetski | 0.5 | 0.5 | 0 | 2021-02-11 | 2021-02-12 | passed |  |  | 211/27963 | 2019/ 2016EXP / Belarus Standart Time | Win10/Chrome | OFF/OFF/ON/OFF | English | Belarus Standard Time
| TC-003090 "Item editor in asset column of Usage Condition Table Editor" | Pavel Niadvetski | 0.05 | 0.05 | 0 | 2021-02-11 | 2021-02-12 | passed |  |  | 211/27963 | 2019/ 2016EXP / Belarus Standart Time | Win10/Chromium | OFF/OFF/ON/OFF | English | Belarus Standard Time
| TC-003069 "Define CUI Location for Toolbar above Usage Condition Table Editor" | Pavel Niadvetski | 0.05 | 0.05 | 0 | 2021-02-11 | 2021-02-12 | passed |  |  | 211/27963 | 2019/ 2016EXP / Belarus Standart Time | Win10/Firefox78 | OFF/OFF/ON/OFF | English | Belarus Standard Time
| TC-003070 "Define a CUI Location for Context Menu of Usage Condition Table" | Pavel Niadvetski | 0.1 | 0.1 | 0 | 2021-02-11 | 2021-02-12 | passed |  |  | 211/27963 | 2019/ 2016EXP / Belarus Standart Time | Win10/Firefox68 | OFF/OFF/ON/OFF | English | Belarus Standard Time
| F-001843 Component and Breakdown Item need to be versionable | kseniya Gavrilenko | 0.2 | 0.2 | 0 | 2021-02-11 | 2021-02-11 | passed |  |  | 211/27963 | 2019/ 2016EXP / Belarus Standart Time | Win10/Chrome | OFF/OFF/ON/OFF | English | Belarus Standard Time
| I-024740 Prevent same child item multiple times on a parent | Pavel Niadvetski | 0.1 | 0.1 | 0 | 2021-02-11 | 2021-02-12 | passed |  |  | 211/27963 | 2019/ 2016EXP / Belarus Standart Time | Win10/Chromium | OFF/OFF/ON/OFF | English | Belarus Standard Time
|  | Total Hours for All | 6.97 | 7.12 | 0.15 |  | Tests Number | 27
|  | % Complete | 100 |  |  |  | Executed Tests | 27
|  | Time Left | 0 |  |  |  | Among them Failed | 0
|  | FAILED | test failed
|  | FAILED | product failed
|  | FAILED | client change
|  | FAILED | infrastructure troubles

## #95 from Azure Devops
N | Tests | Owner | Planned Hours | Actual Hours | Correction | Plan (Finish) | Actual (Finish) | Result | Issues | Functionality issues(not by test) | Solution Build / Innovator build | Server / SQL Server Version | Client OS / Browser | GDPR/Splitscreen/snapshot modes | Client Lang | Client TZ
VM Sample 12SP12
| VM_Sample_Smoke_Dictionary for Product Variability | Olena Zaporozhets | 0.1 | 0.1 |  | 2021-02-15 | 2021-02-16 | passed |  |  | #95 |  | Win10/Chrome | OFF/OFF/OFF/OFF
| VM Sample Smoke test_Variability_Item | Olena Zaporozhets | 0.72 | 1 | 0.28 | 2021-02-15 | 2021-02-15 | failed |  |  | #95 |  | Win10/Firefox78 | OFF/OFF/OFF/OFF
| VM Sample Smoke test_Breakdown_Item | Pavel Niadvetski | 0.5 |  |  | 2021-02-15 | 2021-02-15 | passed |  |  | #95 |  | Win10/Chromium | OFF/OFF/OFF/OFF
| VM Sample Smoke test_Variable Component | Olena Zaporozhets | 0.5 | 0.6 | 0.1 | 2021-02-15 | 2021-02-16 | passed |  |  | #95 |  | Win10/Firefox68 | OFF/OFF/OFF/OFF
| Method for update relationships from vm_ExpressionDefinition | Olena Zaporozhets | 0.2 | 0.5 | 0.3 | 2021-02-15 | 2021-02-16 | passed |  |  | #95 |  | Win10/Chrome | OFF/OFF/OFF/OFF
| VM Sample_Variability Item_Table Rule Editor | Olena Zaporozhets | 0.2 | 0.3 | 0.1 | 2021-02-15 | 2021-02-15 | passed |  |  | #95 |  | Win10/Firefox78 | OFF/OFF/OFF/OFF
|  | Total Hours for All | 2.22 | 2.5 | 0.78 |  | Tests Number | 2
|  | % Complete | #REF! |  |  |  | Executed Tests | 1
|  | Time Left | #REF! |  |  |  | Among them Failed | #REF!
|  | FAILED | test failed
|  | FAILED | product failed
|  | FAILED | client change
|  | FAILED | infrastructure troubles

## Selenium (hidden)
Innovator version | Inn 12.0 SP6 | [5 empty] | Inn 12.0 SP7
Innovator build | 19459 |  | 19775 |  | 20292 |  | 19460 |  | 19777
Test | Test Name | RESULT | Test Name | RESULT | Test Name | RESULT | Test Name | RESULT | Test Name | RESULT | Test Name | RESULT | Test Name | RESULT | Test Name | RESULT
CAD Documents Smoke | PLM_00_001_CadDocuments_CreateDocuments | PASSED | PLM_00_001_CadDocuments_CreateDocuments | PASSED | PLM_00_001_CadDocuments_CreateDocuments | PASSED | PLM_00_001_CadDocuments_CreateDocuments |  | PLM_00_001_CadDocuments_CreateDocuments |  | PLM_00_001_CadDocuments_CreateDocuments |  | PLM_00_001_CadDocuments_CreateDocuments |  | PLM_00_001_CadDocuments_CreateDocuments
CAD Documents Smoke | PLM_00_001_CadDocuments_AddToChanges | PASSED | PLM_00_001_CadDocuments_AddToChanges | PASSED | PLM_00_001_CadDocuments_AddToChanges | PASSED | PLM_00_001_CadDocuments_AddToChanges |  | PLM_00_001_CadDocuments_AddToChanges |  | PLM_00_001_CadDocuments_AddToChanges |  | PLM_00_001_CadDocuments_AddToChanges |  | PLM_00_001_CadDocuments_AddToChanges
CAD Documents Smoke | PLM_00_001_CadDocuments_AddToParts | PASSED | PLM_00_001_CadDocuments_AddToParts | PASSED | PLM_00_001_CadDocuments_AddToParts | PASSED | PLM_00_001_CadDocuments_AddToParts |  | PLM_00_001_CadDocuments_AddToParts |  | PLM_00_001_CadDocuments_AddToParts |  | PLM_00_001_CadDocuments_AddToParts |  | PLM_00_001_CadDocuments_AddToParts
Simple ECO | ECO_002_SimpleECOTest | PASSED | ECO_002_SimpleECOTest | PASSED | ECO_002_SimpleECOTest | PASSED | ECO_002_SimpleECOTest |  | ECO_002_SimpleECOTest |  | ECO_002_SimpleECOTest |  | ECO_002_SimpleECOTest |  | ECO_002_SimpleECOTest
Express DCO Smoke | ExprDCO_002_ExpressDCOTest | PASSED | ExprDCO_002_ExpressDCOTest | PASSED | ExprDCO_002_ExpressDCOTest | PASSED | ExprDCO_002_ExpressDCOTest |  | ExprDCO_002_ExpressDCOTest |  | ExprDCO_002_ExpressDCOTest |  | ExprDCO_002_ExpressDCOTest |  | ExprDCO_002_ExpressDCOTest
Express ECO Smoke | ExprECO_002_ExpressECOTest | PASSED | ExprECO_002_ExpressECOTest | PASSED | ExprECO_002_ExpressECOTest | PASSED | ExprECO_002_ExpressECOTest |  | ExprECO_002_ExpressECOTest |  | ExprECO_002_ExpressECOTest |  | ExprECO_002_ExpressECOTest |  | ExprECO_002_ExpressECOTest
Simple MCO Smoke | MCO_002_SimpleMCOTest | PASSED | MCO_002_SimpleMCOTest | PASSED | MCO_002_SimpleMCOTest | PASSED | MCO_002_SimpleMCOTest |  | MCO_002_SimpleMCOTest |  | MCO_002_SimpleMCOTest |  | MCO_002_SimpleMCOTest |  | MCO_002_SimpleMCOTest
Part Smoke | P_001_1_CreatePartAndAddBOMRelationship | PASSED | P_001_1_CreatePartAndAddBOMRelationship | PASSED | P_001_1_CreatePartAndAddBOMRelationship | PASSED | P_001_1_CreatePartAndAddBOMRelationship |  | P_001_1_CreatePartAndAddBOMRelationship |  | P_001_1_CreatePartAndAddBOMRelationship |  | P_001_1_CreatePartAndAddBOMRelationship |  | P_001_1_CreatePartAndAddBOMRelationship
Part Smoke | P_001_2_ChecksCostsLinks | PASSED | P_001_2_ChecksCostsLinks | PASSED | P_001_2_ChecksCostsLinks | PASSED | P_001_2_ChecksCostsLinks |  | P_001_2_ChecksCostsLinks |  | P_001_2_ChecksCostsLinks |  | P_001_2_ChecksCostsLinks |  | P_001_2_ChecksCostsLinks
Part Smoke | P_001_3_UpdatesParts | PASSED | P_001_3_UpdatesParts | PASSED | P_001_3_UpdatesParts | PASSED | P_001_3_UpdatesParts |  | P_001_3_UpdatesParts |  | P_001_3_UpdatesParts |  | P_001_3_UpdatesParts |  | P_001_3_UpdatesParts
PASSED
FAILED

## TestPlatforms
Server OS / SQL Server Vesion/ TZ | Client OS / Browser | Browser |  | TimeZone | on Mac
2008R2 / 2008 / Belarus Standard Time | MAC (10.14)/Chrome | CHROME |  | Belarus Standard Time | Eastern European Time (UTC +2)
2008R2 / 2012 / Belarus Standard Time | MAC (10.14)/FF60 | FF |  | W. Europe Standart Time (UTC+1) | China Standard Time (UTC +8)
2008R2 / 2014 / Belarus Standard Time | Win10/Chrome | CHROME |  | Central European Standard Time (UTC+1) | Eastern Standard Time (UTC -5)
2008R2 / 2016 / Belarus Standard Time | Win10/Edge18 | EDGE |  | Central Europe Standard Time (UTC+1) | Pacific Standard Time (UTC -8)
2008R2 / 2016EXP / Belarus Standart Time | Win10/Edge17 | EDGE |  | Greenwich Daylight Time (UTC+0) | Indian Standard Time (UTC +5:30)
2008R2 / 2017 / Belarus Standart Time | Win10/FF60 | FF |  | Central Time Zone (UTC -6) | Central European Time Standard Time
2012R2 / 2008 / Belarus Standard Time | Win10/IE11 | IE |  | Pacific Standard time (UTC -8) | Central European Time Standard Time
2012R2 / 2012 / Belarus Standard Time | Win7/Chrome | CHROME |  | Eastern Standard Time (US & Canada)(UTC-05) | Japan Standard Time (UTC +9)
2012R2 / 2014 / Belarus Standard Time | Win7/FF60 | FF |  | Tokyo Standard Time (UTC+9)
2012R2 / 2016 / Belarus Standard Time | Win7/IE11 | IE |  | China Standard Time (UTC+8)
2012R2 / 2016EXP / Belarus Standart Time | Win8.1/Chrome | CHROME |  | India Daylight Time (UTC+5:30)
2012R2 / 2017 / Belarus Standart Time | Win8.1/FF60 | FF |  | FLE Daylight Time (UTC+2)
2016 De / 2017 De/ Central European Time Zone | Win8.1/IE11 | IE
2016 Fr / 2017 Fr / Central European Standard Time
2012R2 JPN / 2012 JPN /Tokyo Standard Time (UTC +9)
2016 / 2008 / Belarus Standard Time
2016 / 2012 / Belarus Standard Time
2016 / 2014 / Belarus Standard Time |  |  | England, Germany, Tokio 3 major areas in USA
2016 / 2016 / Belarus Standard Time
2016 / 2016EXP / Belarus Standart Time
2016 / 2017 / Belarus Standart Time
Cluster / 2012 / Belarus Standard Time
FIPS mode
From Innovator 12.0SP2 | For Innovator 12.0SP12
2012R2 / 2012 / Belarus Standard Time | Client OS / Browser | Browser
2012R2 / 2014 / Belarus Standard Time | MAC (10.14)/Chrome | CHROME |  | TimeZone | on Mac
2012R2 / 2016 / Belarus Standard Time | MAC (10.14)/FF78 | FF |  | Belarus Standard Time | Eastern European Time (UTC +2)
2012R2 / 2016EXP / Belarus Standart Time | MAC (10.14)/FF68 | FF |  | W. Europe Standart Time (UTC+1) | China Standard Time (UTC +8)
2012R2 / 2017 / Belarus Standart Time | Win10/Chrome | CHROME |  | Central European Standard Time (UTC+1) | Eastern Standard Time (UTC -5)
2016 De / 2017 De/ Central European Time Zone | Win10/Chromium | CHROMIUM |  | Central Europe Standard Time (UTC+1) | Pacific Standard Time (UTC -8)
2016 Fr / 2017 Fr / Central European Standard Time | Win10/FF78 | FF |  | Greenwich Daylight Time (UTC+0) | Indian Standard Time (UTC +5:30)
2012R2 JPN / 2012 JPN /Tokyo Standard Time (UTC +9) | Win10/FF68 | FF |  | Central Time Zone (UTC -6) | Central European Time Standard Time
2016 / 2012 / Belarus Standard Time | Win8.1/Chrome | CHROME |  | Pacific Standard time (UTC -8) | Central European Time Standard Time
2016 / 2014 / Belarus Standard Time | Win8.10/Chromium | CHROMIUM |  | Eastern Standard Time (US & Canada)(UTC-05) | Japan Standard Time (UTC +9)
2016 / 2016 / Belarus Standard Time | Win8.1/FF78 | FF |  | Tokyo Standard Time (UTC+9)
2016 / 2016EXP / Belarus Standart Time | Win8.1/FF68 | FF |  | China Standard Time (UTC+8)
2019 / 2012 / Belarus Standart Time |  |  |  | India Daylight Time (UTC+5:30)
2019 / 2014 / Belarus Standart Time |  |  |  | FLE Daylight Time (UTC+2)
2019 / 2016 / Belarus Standart Time
2019/ 2016EXP / Belarus Standart Time
2019/ 2017 / Belarus Standart Time
Cluster / 2012 / Belarus Standard Time
FIPS mode
From Innovator 12.0SP8 | Fro Grammer |  |  | From Innovator 12.0SP8 | Fro Grammer | Fro Grammer | From Innovator 12.0SP8
Server OS / SQL Server Vesion/ TZ | Client OS / Browser | Browser |  | TimeZone | GDPR/ Snapshot / https / SAML | Client Language | 2012R2 / 2012 / Belarus Standard Time
2012R2 / 2012 / Belarus Standard Time | Win10/Chrome | CHROME |  | Belarus Standard Time | OFF/OFF/OFF/OFF | English | 2012R2 / 2014 / Belarus Standard Time
2012R2 / 2014 / Belarus Standard Time | Win10/Edge | EDGE |  | W. Europe Standart Time (UTC+1) | OFF/OFF/ON/OFF |  | 2012R2 / 2016 / Belarus Standard Time
2012R2 / 2016 / Belarus Standard Time | Win10/FF78 | FF |  | Central European Standard Time (UTC+1) |  |  | 2012R2 / 2016EXP / Belarus Standart Time
2012R2 / 2016EXP / Belarus Standart Time | Win10/FF68 | FF |  | Central Europe Standard Time (UTC+1) |  |  | 2012R2 / 2017 / Belarus Standart Time
2012R2 / 2017 / Belarus Standart Time |  |  |  | Greenwich Daylight Time (UTC+0) |  |  | 2016 De / 2017 De/ Central European Time Zone
2012R2 / 2019 / Belarus Standart Time |  |  |  | Central Time Zone (UTC -6) |  |  | 2016 Fr / 2017 Fr / Central European Standard Time
2016 De / 2017 De/ Central European Time Zone |  |  |  | Pacific Standard time (UTC -8) |  |  | 2012R2 JPN / 2012 JPN /Tokyo Standard Time (UTC +9)
2016 Fr / 2017 Fr / Central European Standard Time |  |  |  | Eastern Standard Time (US & Canada)(UTC-05) |  |  | 2016 / 2012 / Belarus Standard Time
2012R2 JPN / 2012 JPN /Tokyo Standard Time (UTC +9) |  |  |  | Tokyo Standard Time (UTC+9) |  |  | 2016 / 2014 / Belarus Standard Time
2016 / 2012 / Belarus Standard Time |  |  |  | China Standard Time (UTC+8) |  |  | 2016 / 2016 / Belarus Standard Time
2016 / 2014 / Belarus Standard Time |  |  |  | India Daylight Time (UTC+5:30) |  |  | 2016 / 2016EXP / Belarus Standart Time
2016 / 2016 / Belarus Standard Time |  |  |  | FLE Daylight Time (UTC+2) |  |  | 2019 / 2012 / Belarus Standart Time
2016 / 2016EXP / Belarus Standart Time |  |  |  | Ukraine Standart Time (UTC+2) |  |  | 2019 / 2014 / Belarus Standart Time
2016 / 2017/ Belarus Standart Time | [6 empty] | 2019 / 2016 / Belarus Standart Time
2016 / 2019 / Belarus Standart Time | [6 empty] | 2019/ 2016EXP / Belarus Standart Time
2019 / 2012 / Belarus Standart Time | [6 empty] | 2019/ 2017 / Belarus Standart Time
2019 / 2014 / Belarus Standart Time | [6 empty] | Cluster / 2012 / Belarus Standard Time
2019 / 2016 / Belarus Standart Time | [6 empty] | FIPS mode
2019 / 2016EXP / Belarus Standart Time
2019 / 2017 / Belarus Standart Time
2019 / 2019 / Belarus Standart Time
2012 / 2017 / Belarus Standart Time
2012 / 2014 / Belarus Standart Time
2012 / 2012 / Belarus Standart Time
2012 / 2016 / Belarus Standart Time
2012 / 2019 / Belarus Standart Time
Cluster / 2012 / Belarus Standard Time
FIPS mode

## Time_Zones_Test_Matrix
|  |  | Client | [5 empty] | Server
Pass/Fail | Prompt | Assignee | Time Zone | Offset | OS | OS Language | Browser | Browser Language | Time Zone | Offset | OS | OS Language
|  |  | GMT Standard Time | UTC+00:00 | Windows | English | IE11 | English | GMT Standard Time | UTC+00:00 | Windows | English
|  |  | Greenwich Daylight Time | UTC+00:00 | Mac | English | Chrome | English | Greenwich Daylight Time | UTC+00:00 | Windows | English
|  |  | Central Europe Standard Time | UTC+01:00 | Windows | English | EDGE | English | Central Europe Standard Time | UTC+01:00 | Windows | German
|  |  | Central European Standard Time | UTC+01:00 | Windows | German | FF52ESR | German | Central Europe Standard Time | UTC+01:00 | Windows | English
|  |  | Tokyo Standard Time | UTC+09:00 | Windows | Japanese | IE11 | Japanese | Tokyo Standard Time | UTC+09:00 | Windows | Japanese
|  |  | Tokyo Standard Time | UTC+09:00 | Windows | Japanese | FF45ESR | Japanese | Tokyo Standard Time | UTC+09:00 | Windows | Japanese
|  |  | Tokyo Standard Time | UTC+09:00 | Windows | English | IE11 | English | Tokyo Standard Time | UTC+09:00 | Windows | Japanese
|  |  | Tokyo Standard Time | UTC+09:00 | Mac | English | FF52ESR | English | Tokyo Standard Time | UTC+09:00 | Windows | Japanese
| Yes |  | Tokyo Standard Time | UTC+09:00 | Windows | Japanese | IE11 | Japanese | Tokyo Standard Time | UTC+09:00 | Windows | English
| No |  | Tokyo Standard Time | UTC+09:00 | Windows | Japanese | FF45ESR | Japanese | Tokyo Standard Time | UTC+09:00 | Windows | English
| No |  | Tokyo Standard Time | UTC+09:00 | Windows | Japanese | Chrome | Japanese | Tokyo Standard Time | UTC+09:00 | Windows | English
| No |  | Eastern Standard Time | UTC-05:00 | Windows | English | IE11 | English | Eastern Standard Time | UTC-05:00 | Windows | English
|  |  | Central Time Zone | UTC-06:00 | Windows | English | EDGE | English | Pacific Standard Time | UTC-08:00 | Windows | English
|  |  | Pacific Standard Time | UTC-08:00 | Mac | English | Crome | English | Central Time Zone | UTC-06:00 | Windows | English
|  |  | Libya Standard Time | UTC+02:00 | Windows | English | IE11 | English | Kaliningrad Standard Time | UTC+02:00 | Windows | English
|  |  | Kaliningrad Standard Time | UTC+02:00 | Windows | Japanese | FF52ESR | English | Libya Standard Time | UTC+02:00 | Windows | English
| No |  | South Africa Standard Time | UTC+02:00 | Windows | French | Chrome | French | South Africa Standard Time | UTC+02:00 | Windows | English
| Yes |  | South Africa Standard Time | UTC+02:00 | Windows | French | FF45ESR | French | South Africa Standard Time | UTC+02:00 | Windows | English
| No |  | Egypt Standard Time | UTC+02:00 | Windows | English | FF52ESR | English | Egypt Standard Time | UTC+02:00 | Windows | French
|  |  | Arabic Standard Time | UTC+03:00 | Mac | English | Chrome | English | Arabic Standard Time | UTC+03:00 | Windows | English
|  |  | Arab Standard Time | UTC+03:00 | Windows | English | IE11 | English | Arab Standard Time | UTC+03:00 | Windows | English
| Yes |  | Omsk Standard Time | UTC+06:00 | Windows | English | EDGE | English | Omsk Standard Time | UTC+06:00 | Windows | English
|  |  | N. Central Asia Standard Time | UTC+06:00 | Windows | Japanese | IE11 | English | N. Central Asia Standard Time | UTC+06:00 | Windows | English
|  |  | AUS Eastern Standard Time | UTC+10:00 | Windows | English | FF45ESR | English | AUS Eastern Standard Time | UTC+10:00 | Windows | English
|  |  | Tasmania Standard Time | UTC+10:00 | Windows | English | IE11 | English | Tasmania Standard Time | UTC+10:00 | Windows | English
|  |  | Central Pacific Standard Time | UTC+11:00 | Windows | English | FF52ESR | English | Russia Time Zone 10 | UTC+11:00 | Windows | English
|  |  | Bougainville Standard Time | UTC+11:00 | Mac | English | Chrome | English | Central Pacific Standard Time | UTC+11:00 | Windows | Japanese
|  |  | Russia Time Zone 10 | UTC+11:00 | Windows | English | FF45ESR | English | Russia Time Zone 10 | UTC+11:00 | Windows | English
|  |  | Norfolk Standard Time | UTC+11:00 | Windows | Japanese | IE11 | English | Norfolk Standard Time | UTC+11:00 | Windows | English
|  |  | US Eastern Standard Time | UTC-05:00 | Windows | English | EDGE | English | US Eastern Standard Time | UTC-05:00 | Windows | English
|  |  | US Mountain Standard Time | UTC-07:00 | Windows | English | FF52ESR | English | US Mountain Standard Time | UTC-07:00 | Windows | English
|  |  | Vladivostok Standard Time | UTC+10:00 | Windows | Japanese | IE11 | English | Vladivostok Standard Time | UTC+10:00 | Windows | English
|  |  | Cen. Australia Standard Time | UTC+09:30 | Windows | English | EDGE | English | Cen. Australia Standard Time | UTC+09:30 | Windows | Japanese
|  |  | Cape Verde Standard Time | UTC-01:00 | Windows | English | IE11 | English | Cape Verde Standard Time | UTC-01:00 | Windows | English
|  |  | SA Pacific Standard Time | UTC-05:00 | Mac | English | FF45ESR | English | SA Pacific Standard Time | UTC-05:00 | Windows | English
Language
English
Japanese
French
German

## QA Team
QA Team Members | Team | Vacation
Eugeniya Semashko | Standard Solutions Lead
Olena Zaporozhets
Pavel Niadvetski
Kseniya Gavrilenko | optionally